## Sheet1
B
ABLEKUMA CENTRAL MUNICIPAL ASSEMBLY
2024 COMPOSITE ACTION PLAN
S/ No | Development Dimension | Objectives | Activities (Operations) | Location | Baseline | Output Indicators | Quarterly Time Schedule |  |  |  | Indicative Budget |  |  |  | Implementing Agency
[7 empty] | 1st | 2nd | 3rd | 4th | DACF | GoG | IGF | Donor | Lead | Collaborating
1 | Social Development | To reduce Gender based inequalities and discrimination for girls/ and boys and build the capacity of women in the area of politics | Monitoring Gender activities carried out by Departments and Units Organize Sensitization Programmes (violence against boys and girls, women participation in Local Government Elections) | Municipal Wide | Nil | Report | [6 empty] | 8800 |  | Gender Desk Officer | All Depts & Units
2 | Governance, Corruption and Public Accountability | To reach out to 1500 People from CBOs,FBOs,PWD AND SCHOOLS | Education of citizens on key topics and pandemics(Good Citizenship, Sanitation, Duties of a citizen, Violent Extremism, Political Tolerance and peaceful co-existence, Gender Equality, Outbreak of Choleria and Mlaria , Tax Education, etc.) | Municipal wide | 386 | 16,800 People from FBOs,CBOs,PWDs and Schools Educated by Dec. 2023 | [6 empty] | 22000 |  | NCCE | Information Service, Gender Desk
3 | Governance, Corruption and Public Accountability | To reach out to 2015 Pupils from CBOs,FBOs,PWD and both Public and Government Schools. | Citizenship Week Celebration, Constitutution Quiz ( Smart Governors), Promote Youth participation | Municipal wide | 39 | 2,015 People from FBOs,CBOs,PWDs, MA and Schools Reached and Educated | [6 empty] | 20000 |  | NCCE
4 | Governance, Corruption and Public Accountability | To reach out to 1830 People from CBOs,FBOs, women, chiefs & queen mothers and PWDs | Education on 2024 Elections, election violence and promoting value and norms in our society | Municipal wide |  | To reach out to 1,800 People from CBOs,FBOs, women and PWD were educated. one day workshop for chiefs and queen mothers | [6 empty] | 16000 |  | NCCE | Social welfare DPT, Central Admin
5 | Governance, Corruption and Public Accountability | Ensure the Registeration of all births and Deaths | Register all live births and deaths in the Assembly, Replace outdated and missing Birth certificates | Lartebiokorshie | 214 | No. of births and deaths registered by the end of the year | [6 empty] | 2000 |  | Birth and Deaths
6 | Governance, Corruption and Public Accountability | Strengthen domestic resource mobilization | Gazetting 2024 fee-fixing resolution and rate inputs.Discuss 2025 fee-fixing | Accra |  | Gazetted fee-fixing on file. |  |  |  |  | 60000 |  | 100000 |  | Budget | Admin
7 | Governance, Corruption and Public Accountability | Strengthen domestic resource mobilization | Update properties and BOP data.Cleaning of valuation data and exhibiting within the municipality. | Municipal wide |  | Revenue Bills produced and distributed |  |  |  |  | 80000 |  |  |  | Budget | PPD/Admin/Finance
8 | Governance, Corruption and Public Accountability | Strengthen domestic resource mobilization | Conduct Budget hearing and consultative meetings with rate payers. | Municipal wide |  | Minutes and attendance on file | [6 empty] | 144000 |  | Budget | Admin /F&A sub- committee
9 | Governance, Corruption and Public Accountability | Strengthen Fiscal Decentralisation | Conduct revenue monitoring/ Supervision exercise and review revenue contract | Municipal-wide | 4 | No. of monitoring exercise and review contract reviews undertaken |  |  |  |  | 11000 | - | - | - | Finance Dept. | Budget Unit, Int. Audit Unit, Revenue Task Force
10 | Governance, Corruption and Public Accountability | Strengthen Fiscal Decentralisation | Prepare and Submit Monthly, Quarterly and Annual Financial Statements | Laterbiokorshie | 13 | No. of Financial Statements prepared and submitted |  |  |  |  | 6000 | - | - | - | Finance Dept. | Budget Unit, Int. Audit Unit
11 | Governance, Corruption and Public Accountability | To confirm that payroll function is properly controlled and operating efficiently. | Personnel Audit | Laterbiokorshie |  | Payroll function is properly controlled and operating efficiently |  |  |  |  | 0 | 0 | 2812.5 | 0 | IAU | HR
12 | Governance, Corruption and Public Accountability | To ensure that there is value for money | Expenditure and Cash management | Laterbiokorshie |  | report prepared and submitted |  |  |  |  | 0 | 0 | 1406.25 | 0 | IAU
13 | Governance, Corruption and Public Accountability | To ensure transparency in the management of affairs | Special Audit ,Procurement and Contract Audit | Laterbiokorshie |  | report on special audit prepared and submitted |  |  |  |  | 0 | 0 | 4500 | 0 | IAU
14 | Governance, Corruption and Public Accountability | Ensure that monies collected on behalf of the Assembly is duly accounted for. | Undertake field audit of revenue. | Laterbiokorshie |  | All cash collected is accounted for |  |  |  |  | 0 | 0 | 7875 | 0 | IAU | Management and revenue head.
15 | Governance, Corruption and Public Accountability | to ensure the efficient and effective running of the Assembly | Facilitate the procurement and supply of goods and services | municipal wide |  | office goods and services procured and supplied | [6 empty] | 876000 |  | procurement Unit | central Admin
16 | Governance, Corruption and Public Accountability | to have a reliable procurement database and foster the purchase of goods and services | Organise 5 tender committee Meetings and prepare & update procurement Plan | municipal wide |  | procurement plan updated and in-use | [6 empty] | 20000 |  | procurement Unit | works, planning unit, Admin
17 | Governance, Corruption and Public Accountability | Promote Road Safety Activities | Education in Schools, transport stations, etc on Road safety issues Provide and manage Road Safety (road signs and signals) in the Municipality | Muncipal-wide | Nil | 3 Education Programmes organised in schools and transport Terminals | [6 empty] | 25000 |  | Transport Officer | MPCU members
18 | Governance, corruption and public accountability | Enhance Transport networks and accessibility | Plan, provide and manage on-street parking in the Municipality Collect data and manage operations of Transport operators | Muncipal-wide | Nil | 10 On-Street Parking streets assigned, operationalized and managed. Data on transport operators and vehicles updated and enforcement done. | [6 empty] | 25000 |  | Transport Officer | MPCU members, Regional Urban Roads, Transport Groups
19 | Environment, Infrastructure and Human Settlement | To promote infrastructural development in the Municipality | Construction of schools / health centre/market/admistration block for AbCMA. Construction of Library and ICT Complex at Blacksmith cluster of schools | municipal-wide |  | identification & acquisition of land and construction of the projects by Dec 2024 |  |  |  |  | 4000000 | 6000000 | 16570 |  | Works
20 | Environment, Infrastructure and Human Settlement | Planning, Budgeting, Monitoring and Evaluation | Update Data on existing Public buildings / Developers buildings in the District (Inventory exercise) | Municipal wide |  | Data on buildings in the District updated |  |  |  |  | 0 | 0 | 360000 | 0 | Works
21 | Environment, Infrastructure and Human Settlement | To ensure development control in the Municipality is enhanced | Initiate the process to prepare EPA permits, screening, integrity reports, Geotech and othe statutory documents, Health & Safety report | Laterbiokorshie |  | Development control activities improved and issues addressed |  |  |  |  | 0 | 0 | 1350000 | 0 | Works | Physical Planning
22 | Environment, Infrastructure and Human Settlement | To facilitate infrastructure development | Facilitate/Supervise the implementation of Public Investment Plan | Laterbiokorshie |  | Projects Drawings, bills of quantities and tender documents prepared. |  |  |  |  | 0 | 0 | 360000 | 0 | Works
23 | Environment, Infrastructure and Human Settlement | To ensure that the safety and due processes of projects are conformed to. | Facilitate the Acquisition permits for Project | Laterbiokorshie |  | Screening and EPA for all projects done |  |  |  |  | 0 | 0 | 270000 | 0 | Works | EPA
24 | Economic Development | To Promote job creation and decent work | Recruitment and deployment under YEA modules, Monitoring and Evaluation of YEA personnel | Municipal wide |  | Youth employed and trained | [6 empty] | 20000 |  | YEA | ABCMA
25 | Environment, Infrastructure and Human Settlement | to improve roads and drain facilities | Maintainance of metal Gratings over drains Construction 10km of U-Drains | Municipal-Wide |  | Metal Gratings maintained 10km U-drains constructed |  |  |  |  | 643500 | 0 | 137250 | 0 | URD
26 | Government, Corruption and Public Accountability | Ensure responsive governance and citizen participation in the development dialogue | Collaborate with society organization (CSO’s),NGO’S and other Department to organize sensitization and education programmes | Municipal-Wide | 10 | Sensitization/education report | [6 empty] | 300000 |  | ISD | NCC/CSO’s/NGO’s,EH &SU,SWCD
27 | Government, Corruption and Public Accountability | Ensure responsive governance and citizen participation in the development dialogue | Conduct Market Survey | Municipal-Wide | 4 | Market survey reports published every quarter. | [6 empty] | 30000 |  | ISD | AbCMA
28 | Government, Corruption and Public Accountability | Ensure responsive governance and citizen participation in the development dialogue | Engage the Public /Media to promote programmes, activities and government policies, Sensitization programmes on Pandemic . | Municipal-Wide | 20 | Major activities covered by the print media, sensitization reports prepared | [6 empty] | 350000 |  | ISD | MEDIA/AbCMA, Media,NCCE,GHS, Environmental Health, SW/CD
29 | Implementation, Coordination, Monitoring and Evaluation | Strengthen M&E systems to deliver development outcomes and Develop effective participation and communication for M&E results. Strengthen M&E technical and logistical capacities at all levels. | Coordination of Implemengtation of MTDP and Projects through MPCU and faciltate participatory Inspection, M& E of Projects and Programmes, Prepare Project Concept Notes. Preperation of Annual Progress report for 2023 and quaterly progress reports for 2024. | Laterbiokorshie | 9 | Inspection Reports, Monitoring reports and Evaluation reports drafted. 2023 Annual Progress Report perapred and validated and 4 quarterly Progress Reports that tracks implementation of AAP. |  |  |  |  | 78000 |  | 34000 |  | MPCU | All Depts/Units Inspection team, stakeholders
30 | Implementation, Coordination, Monitoring and Evaluation | Improve participation of civil society in national development | Organize Quarterly Town Hall meetings and other Stakeholder engagements | Laterbiokorshie | 5 | 4 Town Hall Meetings held with participation of 1650 residents |  |  |  |  | 48000 |  | 20000 |  | MPCU | All deps/Units
31 | Implementation, Coordination, Monitoring and Evaluation | Strengthen planning, implementation and coordination capacities at all levels Accelerate promotion Investment potentials of the Muncipality | Facilitate the Preperation of 2025 Composite Annual Action Plan and conduct mid-year review of 2024. Develop Municipal Public Investment Plan and facilitate activities of Entity Project Committee. | Laterbiokorshie | 4 | 2025 Annual Action Plan Drafted , Approved and disseminated . Comprenhensive Public Investment plan detailing all proposed Capital projects for 2022-2025 and approved |  |  |  |  | 30600 |  | 43000 |  | MPCU | All Depts/Units Private Sectors ,Assembly Members , Investors
32 | Implementation, Coordination, Monitoring and Evaluation | Strengthen the implementation of the ocal economic development (LED) and private sector participation | Facilitate the planning and implementation Local Economic Development (LED) interventions | Municipal-wide | 28 | Number of LED Activities Implemented | [6 empty] | 18600 |  | MPCU | Private Sector,Trade Groups, Ass. Members, SWCD,YEA
33 | Environment, Infrastructure and Human Settlement | Strenghten the implementation of the Greater Accra Resilient and Integrated Development Project | Facilitate the Implementation of Drainage O&M for GARID Project (Conduct Survey on infrastructure and develop Asset register for all Assets; Support for Coordination,Meetings & Monitoring & Evaluation; Develop Drainage Network Map; Conduct Survey of all storm, primary and secondary drains; Prepare O&M; Desilting of underground channels; Replacement of slabs and metal gratings) | Municipal-Wide |  | GARID O&M activities implemented | [7 empty] | 420000 | PIU | Works,DUR, GARID, Procurement
34 | Implementation, Coordination, Monitoring and Evaluation | Promote the fight against corruption and economic crimes and mainstream crosscutting issues | Mainstream the National Anti-Corruption Action Plan (NACAP) , 1D1F, AfCFTA, Climate Change and other Government Interventions | Municipal-wide | 2 | 9 sensitisation event held in 7 electoral areas |  |  |  |  | 10000 | 6000 | 15300 |  | MPCU | CSos, ISD ,NCCE, Ass. Members
35 | Environment, Infrastructure and Human Settlement | Promote sustainable spatially integrated development of human settlements | Conduct Spatial Planning Committee Meeting and Technical Sub Committee Meetings | Laterbiokoshie |  | Munites and Attendance |  |  |  |  | 0 | 0 | 200000 |  | PPD | Works
36 | Environment, Infrastructure and Human Settlement | Promote sustainable spatially integrated development of human settlements | Preperation of Spatial Development Framework and Structure plan | Municipal-Wide |  | Spatial Development Framework with Maps and Report, Spatial Structural Plans with Maps and Report |  |  |  |  | 370000 | 0 | 0 |  | PPD
37 | Environment, Infrastructure and Human Settlement | Promote sustainable spatially integrated development of human settlements | Street Naming and Property Addressing System | Municipal-Wide |  | Field Picture Reports |  |  |  |  | 150000 | 0 | 0 |  | PPD
38 | Environment, Infrastructure and Human Settlement | Promote sustainable spatially integrated development of human settlements | Monitoring of physical developments to ensure conformity with Local Plans Public Education on Permit Schemes, process etc | Municipal-Wide |  | Monitoring embarked and monitoring reports prepared 1 number Education on Permit Shemes for developers & maps of flood zones and telcom masts printed |  |  |  |  | 0 | 52000 | 100000 |  | PPD | Works
39 | Social Development | Improve Family planning access and use | Provide SBCC/ACSM/ health talks on FP at OPDs in all Public health facilities. Display family planning commodities at all outreaches and during home visits. Request and make available, FP commodities at all times at all service provision points in the municipality. Capacity building of all staff in Family planning service provision | DHMT | 1.6% | Family Planning Acceptors increased by 20% Improved CYP. All staff trained in Family planning service provision and bi-annual refresher training established. | [6 empty] | 8000 |  | MHD
40 | Social Development | To improve quality of health services provided at CHPS zones | Training of CHOs on EPI, disease surveillance (AFP, measles, yellow fever, malaria, TB, HIV etc). Make all demarcated CHPS zones functional/ operational, Procurement of needed logistics. Procurement of basic equipment for 52 CHPS Zones | DHMT | 15 functional CHPS Zones 52 CHPS Zones without basic equipment | CHPS zones increased by 25 and fully operational. Basic equipment (chairs, tables, weighing scales/stands, infantometers, homevsiting bags, bp apparatus, glucometer, immunisation tray, screens, oil cloth, jute bags etc. procured and supplied to all 52 CHPS Zones | [6 empty] | 5000 |  | MHD
41 | Social Development |  | Operationalization of the Polyclinic. Capacity building of staff on clinical and public health service delivery, emergency preparedness and handling of emergencies. | Muncipal-wide | Nil | Staff well orientated on emergency preparedness and able to handle emergencies, clinical care and public health services. |  |  |  |  | 30.000.00 |  |  |  | MHD
42 | Socoal Development | Establishment of container clinics at vantage points within each sub-district | Engage stakeholders for support and mobilize resource. Draw a plan for the establishment of the clinic and perform a feasibilty and sustainability studies. Procure equipment and logistics | All sub-districts | Nil | Container clinics establihed and fully patronized |  |  |  |  | 40000 | 10000 |  |  | MHD
43 | Social Development | Increase access to mental health | Trainings for CHOs and sensitization of private health facilities on the need to offer mental health services, maintain facility and community-based mental health services | Muncipal-wide | Nil | Mental health services provided |  |  |  |  | 20000 | 40000 |  |  | MHD
44 | Social Development | Improve nutritional status of women, adolescents and children. Establishment of community pregnancy schools. | Sensitization of the public on healthy food practices via FM stations. Strengthen IFA supplementation at schools, community level. Awareness creation on anaemia in pregnancy and among adolescent girls. Register all non ANC attendant pregnant women within the municipal and link then to care Identify a common meeting place, days at clients' convenience. Draw action plan, mobilize resources and organize pregnancy school. | Muncipal-wide | anaemia in pregnancy(36wks) at 27% | Improved data from DHIMS, no. of IFA distributed Improvement in anaemia in pregnancy to 10%. No. of pregnant women registered, schooled and linked to care. |  |  |  |  | 5000 | 6000 |  |  | MHD
45 | Social Development |  | To provide refresher training to all midwives on basic newborn examination, care and resuscitation and provide on-the- job support. To conduct Mortality audits within 7days of occurrence. | Muncipal-wide |  | No. of midwives training conducted no. of mortality audits held |  |  |  |  | 1800 |  |  | 15000 | MHD
46 | Social Development | Intensify prevention and control of communicable diseases and ensure the reduction of HIV/AIDS | Community sensitisation on importance of immunisation. Schedule immunization sessions during school health activities (crèche). Increase awwareness on sexuality and STIs including HIV/AIDS Encourage all clinics and hospital to provide testing and counselling sessions | Muncipal-wide | 27 CWC sessions run weekly CHMC formed | No. immunisation sessions during Sch Health Screening sessions done and reported on, monthly | [8 empty] | MHD
47 | Social Development |  | CATCH UP Campaigns. Organisation of Community Wellness Clinic. | Muncipal-wide |  | Quarterly catch up campaigns done. No. of community welness clinics organised. |  |  |  |  | 42000 |  |  |  | MHD
48 | Social Development | To promote quality teaching and learning & Administrative procedures | Monitoring and evaluation of activities in schools. Data collection and collation (School Census). | Municipal-wide |  | Expect that all teachers have reported in their various schools and have updated all forms of school records and administrative procedures. Schools database updated. |  |  |  |  | 6000 | 30, 000 | 12000 |  | GES
49 | Social Development | To create rapport with Head teachers and to establish boundaries of the Directorate | Familiarization visits to schools and boundaries of AbCMED. Meetings (Teachers, Headteachers, Stakeholders). | Municipal-wide |  | Expect that officers will know the boundaries of operation and also result in collaboration. Meeting Minutes on file. | [6 empty] | 24000 |  | GES | AbCMA
50 | Social Development | To inform officers, teachers and other stakholders about educational policies | Organize orientation and training programs for beneficiaries | Municipal-wide |  | Policies are disserminated |  |  |  |  | 25, 000 |  | 50, 000 |  | GES | AbCMA
51 | Social Development | To appreciate and recognize the efforts of staff. To improve on the reading abilities of learners. To adequately prepare final year students towards the final BECE examination. | Yearly major programs (CODE, ADEOP, Conference, SPAM, CPD, STMIE, My First Day at School, Teacher Awards). Special Competitions (Reading clinics, Spelling B, Quizes, Essay Competitions, etc.). BECE Preparation. | Municipal-wide |  | Show appreciation towards deserving winners. Formation of Reading Clubs in Schools. Schools adeqquately prepared towards BECE. | [6 empty] | 135, 000 |  | GES | AbCMA
52 | Environment, Infrastructure and Human Settlement | to prevent the emergencies/disasters that can arise as a result of collaspesd buildings. | Inspection of on-going projects & delapidated buildings, Fuel stations and safety inspection of expired products in pharmaceutical shops and super markets | municipal wide |  | inspections of buildings/projects done. | [6 empty] | 10000 | 5000 | NADMO | Works
53 | Environment, Infrastructure and Human Settlement | to ensure that the environment is safe from Man-Made Hazards which can cause disasters | Education and sensitization on climate change and its effects in Communities and Schools. | municipal wide |  | community, school and organizational engagements held. | [6 empty] | 3500 | 1336 | NADMO
54 | Environment, Infrastructure and Human Settlement | to ensure that Green AbCMA is implemented. | Embark on green tree planting exercise. Trim/cut down overgrown trees. Maintenance of trees planted during AbCMA tree planting exercise | municipal wide |  | tree planting exercise completed. | [6 empty] | 30000 | 32000 | NADMO | AbCMA
55 | Environment, Infrastructure and Human Settlement | To create awareness on various topics concerning COVID-19 and disaster prevention. | Education and sensitization on Disaster prevention & adaptation in schools and communities | municipal wide |  | survival of all seedlings and replacement of dead ones. | [6 empty] | 15000 | 7000 | NADMO | Planning Office
56 | Governance, Corruption and Public Accountability | Effective Payment and distribution Systems ,POS devices,mobile apps (training on software)and Effective printing of 2024 BOP, Property rate and Signage bills | Set up a system for the introduction of new payment systems for payment of Rate, Fees , Fines, statements and distribution of bill electronicall, Start the process for generating and printing of 2024 BOP, property rate and Signage bills | Laterbiokoshie |  | Payment and distribution Systems created,Generating and printing of 2024 BOP, property rate and signage | [6 empty] | 150000 |  | MIS UNIT | Finance dept.
57 | Governance, Corruption and Public Accountability | Maintainance and Servicing | Run maintenance on photo studio,Website,Records management system,Desktops, laptop computers, printers and photocopier machines | Laterbiokoshie |  | Maintenance done | [6 empty] | 37000 |  | MIS UNIT | Finance dept.
58 | Governance, Corruption and Public Accountability | To take stock of Assembly’s Assets | Update the Asset Stock register of the Assembly | Lartebiokorshie |  | Data on Assets, date purchased, suppliers, and the current state of the asset whether in use or not. | [6 empty] | 7000 |  | Stats | Procurement, Stores, Works
59 | Governance, Corruption and Public Accountability | Data collection on socio-economic sector(i.e. Businesses NGO’s, hospitals, education centers and religious organizations) | Collect and Update existing data of Businesses and properties, NGO’s, schools, Hospitals and religious organizations within the Municipality | Lartebiokorshie |  | Data on public and private schools, health facilities and religious organization also data on businesses and properties | [5 empty] | 2850 |  |  | Stats | Planning, Education,Revenue, Health
60 | SOCIAL DEVELOPMENT | 1. Improve and strengthen the policy and legal environment, institutions and systems for child and family welfare. 2. Strengthen social protection for the vulnerable. | 1.Identify and register PWDs and facilitate skills training for PWDs. 2. Facilitate the implementation of LEAP activities. 3.Supervise and monitor the activities of NGOs. 4.Supervise and monitor the activities of Day care centers. | Municipal Wide |  | 1.Number of Disabled people who have accessed the fund 2. Number of LEAP beneficiaries increased 3. Number of NGOs activities supervised effectively. 4. Number of Early Childhood centers that have been registered and supervised effectively | [5 empty] | 1250 | 7300 |  | SWCD | 1.National Council of Person's with Disabilities 2.LEAP Secretariat and the Paying Financial Institution (Access Bank) 3. NGOs 4. Day Care Centers.
61 | SOCIAL DEVELOPMENT | Promote the rights and welfare of children | Undertake general casework management including support to families and individuals in non-child maintenance case, child abuse, custody and family welfare or reconciliation. | Municipal Wide |  | Number of Child and family welfare cases managed effectively | [5 empty] | 750 | 6700 |  | SWCD | Families, Police and the Family Tribunal Court
62 | SOCIAL DEVELOPMENT | Prevent and protect children from all forms of violence, abuse, neglect and exploitation. | Liase with the police and also prepare social investigation reports in favour of missing, abandoned or vulnerable children. | Municipal Wide |  | Number of Social investigation in favor of missing and abandoned children managed effectively as well as chid protection issues. | [5 empty] | 1050 | 5550 |  | SWCD | Residential homes, Police,Court,Media houses,Hospitals, NGO'S etc.
63 | SOCIAL DEVELOPMENT | 1.Train junior high school students on menstrual hygiene management. 2. Train youth groups and women group in income generating activities such as confectionery making. | 1.Train junior high school students on menstrual hygiene management. 2. Train youth groups and women group in income generating activities such as confectionery making. | Municipal Wide |  | 1.Number of students trained and number of schools reached. 2.Number of women's group trained and number of people reached. | [5 empty] | 950 | 4450 |  | SWCD | Youth groups, FBOs,CBOs and Womens groups.
64 | ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Monitorings by Agric. Director, Agric. officers and MPCU members | Municipalwide |  | All Monitorings carried out | [5 empty] | 4500 | 5400 |  | AGRIC. Dept. | MPCU members
65 | ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Train 30 Farmers on Climate Change Approaches | Municipalwide |  | 30 farmers trained |  |  |  |  | 135500 | 2500 |  |  | AGRIC. Dept. | NADMO
66 | ECONOMIC DEVELOPMENT | Promote livestock and poultry development for food security and income generation | To vaccinate 200 cattle against CBPP by Dec. 2024 To vaccinate 200 dogs and 100 cats against Rabies Carryout PPR vaccination on small ruminants by December 2024. | Municipalwide |  | 200 cattle vaccinated 200 dogs and 100 cats vaccinated | [6 empty] | 8400 |  | AGRIC. Dept. | VD
67 | ECONOMIC DEVELOPMENT | Enhance the application of science, technology and innovation | AEAs Home and Farm visits to extend improved technologies by Dec. 2024 | Municipalwide |  | Home and Farm visits conducted | [6 empty] | 12800 |  | AGRIC. Dept.
68 | ECONOMIC DEVELOPMENT | Strengthen gender mainstreaming, coordination and implementation of gender related interventions in all sectors. | Conduct a gender mapping of activities of all stakeholders to identify their reach, coverage and gaps. | Municipalwide |  | Gender Mapping conducted | [5 empty] | 2500 | 2000 |  | AGRIC. Dept.
69 | ECONOMIC DEVELOPMENT | Strengthen gender mainstreaming, coordination and implementation of gender related interventions in all sectors. | Train Staff on Gender in relation to Agriculture and Education on HIV/AIDS. Train Staff on some common Livestock diseases which affect Productivity of Farmers. | Laterbiokorshie |  | Staff trained | [5 empty] | 5500 | 5100 |  | AGRIC. Dept.
70 | Governance, Corruption and Public Administration | Capacity Building Plan Implementation and reporting | Implement on quarterly basis, planned capacity building interventions and submit 4 quarter reports on capacity building to OHLGS through RCC by the end of 31st December 2024 | Various |  | At least 92% of Planned Capacity Building Interventions implemented and reported on by 31st December, 2024 |  |  |  |  | 50000 | 2500 | 82000 |  | Human Resource
71 | Governance, Corruption and Public Administration | Consultative meeting for the preparatiion of the composite capacity building plan | organise training needs assessment meetings to collate and prepare 2024 composite capacity building plan | Assembly Hall |  | Composite Capacity Building Plan prepared |  |  |  |  | 0 | 0 | 4000 |  | Human Resource
72 | Governance, Corruption and Public Administration | TNT for HRM Reports submission at RCC and OHLGS | Prepare and submit 4 quarterly reports on HRM activities Prepare and submit HRMIS database backups to RCC every month | HR Office |  | 4 quarterly HRM reports on all activities submitted by 15th of the first month of the ensuing quarter Submit monthly updated stafflist and HRMIS database backup by 15th of the ensuing month |  |  |  |  | 0 | 0 | 1900 |  | Human Resource
73 | Governance, Corruption and Public Administration | Interview Fees for GOG Staffs Promotions in 2024 Promotion Interviews and Recruitment (IGF STAFFS | Prepare Promotion register and other documentation in respect of GOG staffs due for promotion in 2024 and submit to RCC. Conduct one (1) recruitment exercise and one (1) Promotion interview for staffs due for Promotions. | Lartebiokorshie |  | All affected staffs documentation prepared and submitted to RCC and fees paid twice in a year. Staffs due for promotion interviewed and promoted. And staffing gaps identified and filled through recruitment interviews. |  |  |  |  | 0 | 0 | 6500 |  | Human Resource
74 | Governance, Corruption and Public Administration | Performance Management and Appraisal planning, Midyear Review and End of Year Evaluation sessions/meetings for HoD's and staffs (Snack & Water) | Supervise the execution of performance management tools and monitor effective compliance | Assembly Hall |  | All HoD's oriented on the planning, midyear and end-of-year evaluation of the PMS and ensure staffs are appraised and evaluated by December, 2024 |  |  |  |  | 0 | 2500 | 0 |  | Human Resource
75 | Governance, Corruption and Public Administration | Organisation of Staff meetings | Organise staff Forum / durber at least twice in the year to provide direct interface between staffs and Management and also take them through aathe Local Gov't Protocols | Assembly Premises |  | At least 2 staff meetings organised: one (1) in each half of the year |  |  |  |  | 0 | 0 | 3000 |  | Human Resource
76 | Social Development | Prevention and behavoral change communication | Sensitization programme for Adolescents ( In and Out School) Organise World AIDs Day | Laterbiokoshie |  | 1 World AIDS Day programme orgnised |  |  |  |  | 7000 |  | 1000 |  | HIV/AIDS FOCAL PERSON | MHD
77 | social development | To promote basic hygiene in schools, regulate and promote sanitary standards in all public toilets, homes, shops and promote safe food for public consumption. | To conduct education to students, teachers and non- teaching staff. To educate market women, traders and community members on the Assembly’s bye-law, operation clean your frontage activities and regularizing tricycle operators | Municipal Wide | 102 schools | School Health education carried out. Education n organized in all market centers, community members sensitized on their duties and responsibilities as enshrined in the bye-law. |  |  |  |  | 64000 |  | 130000 |  | EHSU | Head masters/mistresses, public toilet attendant, Service provider, NADMO, Information services, food handlers, market leaders/queens, traders, religious leaders and procurement.
78 | Socoal Development | To promote basic hygiene and promote safe food for public consumption. | To initiate mass screening and education to food handlers alongside printing of certificates and ceasing and confiscicating expire product. |  | 1611 vendors screened | Mass screening and health education carried out and certificate issued accordingly |  |  |  |  | 50000 |  | 55000 |  | EHSU
79 | social development | To promote health and prevent diseases | Public announcement and sensitization on household toilet contruction and acquisition. 2. Operation clean your frontage activities. To conduct education to public toilet attendants. | Municipal Wide | 129 75 toilet attendants | household toilets constructed. 2. People are made to be responsible of their frontages Education carried out to public toilet attendants and certified as such. |  |  |  |  | 5700 |  | 210000 |  | EHSU | SPI, Information service, works dept., assembly members, Planning unit, dept of social welfare and community development.
80 | social development | To promote and protect health, and to ensure clean healthy environment | To inspect ALL types of premises including markets. To prosecute recalcitrant sanitation offenders and effect bench warrant arrest | Municipal Wide | 15189 | Quarterly reports Sanitary offenders prosecuted and bench warrants effected |  |  |  |  | 80000 |  | 160000 |  | EHSU | Assemblymen, Landlords, Traders
81 | social development | To prevent diseases and promote health | Organize monthly clean up exercise and special clean up exercises, evacuate heaps, drains de-silted and septic tank of public schools dislodge. | Municipal Wide | 18 | Clean up exercise organized municipal wide, Heaps of refuse collected, Tertiary drains improved by 15% and storm drains improved by 25% and all full up septic tanks in public schools dislodged |  |  |  |  | 300000 |  | 469000 |  | EHSU | Assembly members, Community members, Private contractors, and Zoom lion
82 | social development | To prevent piled up refuse in the communities | Monitor and evaluate activities of waste management contractors | Municipal Wide | 75 household registered | Container sites improved by 77% and Collection at domestic level improved by 12%. |  |  |  |  | 100000 |  | 54000 |  | EHSU | Zoomlion and service providers
83 | social development | To protect and promote health | Disinfection and disinfestation of public places including, public toilets, open drains, container sites etc. | Municipal Wide |  | Disinfection and disinfestation carried out in markets, lorry stations, public toilets, Drains, container sites and other public places. |  |  |  |  | 50000 |  | 49000 |  | EHSU | Zoomlion
84 | Economic Development | To Promote Youth Development in the Municipality | Facilitate the Implementation of activities of National Youth Authority | Laterbiokoshie |  | NYA Activities facilitated and embarked | [6 empty] | 50000 |  | National Youth Authority
85 | Economic Development | Diversify and expand the tourism industry for economic development | Participation in Cultural Festivals and Other Customary Activities eg:Homowo Festivals and Exhibition for groups under LED Participation in activities and programs of the Centre for National Culture. Eg. REFAC, NAFAC,ADESA VILLAGE etc | Laterbiokoshie |  | Preserve and Promote Cultural Heritage |  |  |  |  | 7000 |  | 5000 |  | CULTURE AND TOURISM DEPARTMENT
86 | Governance, corruption and Public Accountability | To Deepen Decentratralization | Organize Statutory Meetings (General Assembly, Executive Committee, Sub-Committee's, MUSEC, Audit committee, Management etc.) | Laterbiokorshie | 80 | Meeting minutes | [6 empty] | 250000 |  | Central Admin | HoD's and Assembly Members
87 | Governance, corruption and Public Accountability | To promote community participation in local governance | Stakeholders/community engagement and Sensitization on the mandate of the Assembly in all electoral areas | Municipal-Wide |  | Reports |  |  |  |  | 175000 |  | 60000 |  | Central Administration | Human Resource
88 | Governance, corruption and Public Accountability | To ensure good governance and Promote Tourism in the Municipality | Organize National celebrations and Festivals ( Independence day, Homowo festival etc) | Municipal-Wide |  | Reports |  |  |  |  | 260000 |  | 50000 |  | Central Admin | all Departments
89 | Governance, corruption and Public Accountability | Ensure motivation of Officers and to ensure good governance | Support Assembly Participation in NALAG activities | Laterbiokorkoshie |  | NALAG supported duly and report prepared. | [6 empty] | 50000 |  | Administration | Finance
90 | Governance, corruption and Public Accountability | To ensure good governance and build capacity of Assembly Members | Organize inauguration and orientation workshop for Assembly Members | Lartebiokorshie |  | Reports | [6 empty] | 50000 |  | Central Admiistration | Works Department
91 | Governance, corruption and Public Accountability | For effective monitoring and evaluation To promote smooth running of official vehicles | Protocol activities (monitoring and evaluation teams, etc) Facilitate transport activities (Fuel, maintenance. insurance, tools, other logistics ) | Lartebiokorshie |  | Reports |  |  |  |  | 130000 |  | 330000 |  | Central Admin
92 | Governance, corruption and Public Accountability | To promote security and safe environment | Support for Security activities, Electoral Commision and Legal Issues | Lartebiokorshie |  | Reports |  |  |  |  | 80000 |  | 100000 |  | Central Administration
93 | Governance, corruption and Public Accountability | To create public awareness of marriage registration, educate Marriage Officers and Officiating Ministers on the various types of marriages in Ghana and its legal implications. | Creating awareness on marriage celebration in the Municipality. Organise skills and training development for the various officers and Officiating Ministers. | AbCMA |  | Reports, Increased Revenue | [6 empty] | 97000 |  | Central Administration | Marriage Officer and Information Officer
94 | Governance, corruption and Public Accountability | Promote gender based activities in the Municipality | Support for Gender based activities |  |  | Report | [6 empty] | 20000 |  | Gender Desk Oficcer
95 | Governance, corruption and Public Accountability | To build staff capacity in service delivery | Organize training for Client Service staff on customer relations / service and on service delivered by the Assembly |  |  | Report | [6 empty] | 10000 |  | Central Administration | Human Resource
96 | Governance, corruption and Public Accountability | To ensure good governance in the Municipality | Support activities of Store, Records Management Unit, Disburse funds to Education, Health. |  |  | Report | [6 empty] | 90000 |  | Stores | Central Administration
97 | Governance, corruption and Public Accountability | To strenghten local participation and decentralisation | Support activities of Zonal Councils | Municipal-Wide |  | Zonal Council Reports |  |  |  |  | 74400 |  |  |  | Central Admiistration | Other Departments
[11 empty] | 7170500 | 6140850 | 7646713.75 | 480336

## Sheet3
66 | ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Compile and Submit 4 Quarterly and 1 annual reports by Dec. 2024 | Laterbiokorshie |  | An annual and 4 quarterly report submitted |  | 1000 | 1800 | AGRIC. Dept.
67 | ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Monitorings by Agric. Director, Agric. officers and MPCU members | Municipalwide |  | All Monitorings carried out |  | 4500 | 5400 | AGRIC. Dept. | MPCU members
68 | ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Organize 1 District Agricultural Planning and 1 Review Session with farmers and other stakeholdersr(RELC),one in second quarter and the other in third quarter. | Laterbiokorshie |  | RELC Planning and Review Sessions organized |  |  | 6000 | AGRIC. Dept. | CSIR
70 | ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Raise and Support 100 households with 1000 Layers and Cockerels | Municipalwide |  | 100 Households supported with 1000 birds | 75000
71 | ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Train 30 Farmers on Climate Change Approaches Train and Establish 30 Youth in Rabbit Production | Municipalwide |  | 30 farmers trained and 30 youth established | 135500 | 2500 |  | AGRIC. Dept. | NADMO
73 | ECONOMIC DEVELOPMENT | Promote livestock and poultry development for food security and income generation | To vaccinate 200 cattle against CBPP by Dec. 2024 To vaccinate 200 dogs and 100 cats against Rabies Carryout PPR vaccination on small ruminants by December 2024. | Municipalwide |  | 200 cattle vaccinated 200 dogs and 100 cats vaccinated |  |  | 8400 | AGRIC. Dept. | VD
74 | ECONOMIC DEVELOPMENT | Enhance the application of science, technology and innovation | AEAs Home and Farm visits to extend improved technologies by Dec. 2024 | Municipalwide |  | Home and Farm visits conducted |  |  | 12800 | AGRIC. Dept.
76 | ECONOMIC DEVELOPMENT | Strengthen gender mainstreaming, coordination and implementation of gender related interventions in all sectors. | Conduct a gender mapping of activities of all stakeholders to identify their reach, coverage and gaps. | Municipalwide |  | Gender Mapping conducted |  | 2500 | 2000 | AGRIC. Dept.
78 | ECONOMIC DEVELOPMENT | Enhance the application of science, technology and innovation | A Study tour for Staff and Livestock Farmers on IMO Technologies applied in Livestock Production | Municipalwide |  | Study tour was organized |  |  | 3500 | AGRIC. Dept.
80 | ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Train and Establish 30 PWDs in Mushroom Production Establish a Crop Demonstrations Sensitization on PFJ | Municipalwide |  | 30 PWDs trained and established Crop demonstration done | 35000 | 6500 | 6500 | AGRIC. Dept.
81 | ECONOMIC DEVELOPMENT | Strengthen gender mainstreaming, coordination and implementation of gender related interventions in all sectors. | Train Staff on Gender in relation to Agriculture and Education on HIV/AIDS. Train Staff on some common Livestock diseases which affect Productivity of Farmers. | Laterbiokorshie |  | Staff trained |  | 5500 | 5100 | AGRIC. Dept.
84 | ECONOMIC DEVELOPMENT | Strengthen gender mainstreaming, coordination and implementation of gender related interventions in all sectors. | Organize 2 trainings and demonstrations for 30 women on Soya Khebab, Soya Milk, Soya meanimix preparation | Municipalwide |  | Women trained | 35000 |  |  | AGRIC. Dept.
85 | ECONOMIC DEVELOPMENT | Strengthen gender mainstreaming, coordination and implementation of gender related interventions in all sectors. | Train 30 Females on SOYA Utilization Train and Establish 20 women in Snail Production Train and equip 30 women on affordable poultry housing using locally available resources. | Municipalwide |  | Women trained | 20800 | 7500 | 3500 | AGRIC. Dept.
87 | Governance, Corruption and Public Administration | Capacity Building Plan Implementation and reporting | Implement on quarterly basis, planned capacity building interventions and submit 4 quarter reports on capacity building to OHLGS through RCC by the end of 31st December 2024 | Various |  | At least 92% of Planned Capacity Building Interventions implemented and reported on by 31st December, 2024 | 50000 | 2500 | 82000 | Human Resource
88 | Governance, Corruption and Public Administration | Consultative meeting for the preparatiion of the composite capacity building plan | organise training needs assessment meetings to collate and prepare 2024 composite capacity building plan | Assembly Hall |  | Composite Capacity Building Plan prepared | 0 | 0 | 4000 | Human Resource
89 | Governance, Corruption and Public Administration | TNT for HRM Reports submission at RCC and OHLGS | Prepare and submit 4 quarterly reports on HRM activities Prepare and submit HRMIS database backups to RCC every month | HR Office |  | 4 quarterly HRM reports on all activities submitted by 15th of the first month of the ensuing quarter Submit monthly updated stafflist and HRMIS database backup by 15th of the ensuing month | 0 | 0 | 1900 | Human Resource
91 | Governance, Corruption and Public Administration | Monthly Validation of Salaries and Compensation | Staffs salaries, both GOG and IGF validated and worked on timely to ensure prompt payment of salaries | HR Office |  | 12 monthly salary validation voucher submitted to RCC, Budget Office and Finance Office | 0 | 0 | 2600 | Human Resource
92 | Governance, Corruption and Public Administration | Interview Fees for GOG Staffs Promotions in 2024 Promotion Interviews and Recruitment (IGF STAFFS | Prepare Promotion register and other documentation in respect of GOG staffs due for promotion in 2024 and submit to RCC. Conduct one (1) recruitment exercise and one (1) Promotion interview for staffs due for Promotions. | Lartebiokorshie |  | All affected staffs documentation prepared and submitted to RCC and fees paid twice in a year. Staffs due for promotion interviewed and promoted. And staffing gaps identified and filled through recruitment interviews. | 0 | 0 | 6500 | Human Resource
94 | Governance, Corruption and Public Administration | Support for ILGS or any recognised institution Programme and Scholarships | Provide Support for 3 staff to pursue a programme of study at the ILGS and any recognized institution for academic development | ILGS/Training Centre or any recognised center |  | Selected / Applicable staffs supported in 2024 to pursue programmes | 0 | 0 | 14000 | Human Resource
96 | Governance, Corruption and Public Administration | Performance Management and Appraisal planning, Midyear Review and End of Year Evaluation sessions/meetings for HoD's and staffs (Snack & Water) | Supervise the execution of performance management tools and monitor effective compliance | Assembly Hall |  | All HoD's oriented on the planning, midyear and end-of-year evaluation of the PMS and ensure staffs are appraised and evaluated by December, 2024 | 0 | 2500 | 0 | Human Resource
98 | Governance, Corruption and Public Administration | Staff appreciated at end of year Retirees Honored and Awarded | To appreciate and motivate staff through end of year get-together. Organise Retirement ceremony and Awards for staffs that will be retiring in 2024. | Assembly Hall |  | Staff motivated and appreciated retired staff would be honored and awarded. | 0 | 5000 | 5000 | Human Resource
99 | Governance, Corruption and Public Administration | Organisation of Staff meetings | Organise staff Forum / durber at least twice in the year to provide direct interface between staffs and Management and also take them through aathe Local Gov't Protocols | Assembly Premises |  | At least 2 staff meetings organised: one (1) in each half of the year | 0 | 0 | 3000 | Human Resource
101 | Governance, Corruption and Public Administration | Compensation for staffs who are injured, impaired or suffer deformity in the discharge of their official duties on behalf of the Assembly | Compensation for staffs who are injured, impaired or suffer deformity in the discharge of their official duties on behalf of the Assembly | Assembly Premises |  | Affected staff supported | 0 | 0 | 3000 | Human Resource
102 | Social Development | Reduce the incidence of new HIV, AIDS/STIs and other infections, especially among vulnerable groups | Sensitization programme for Adolescents ( In and Out School), Churches and Mosques | Abossey Okai, Sukura and Laterbiokoshie | 2 | 3 BASIC SCHOOLS SENSITIZED | 10000 |  | 5000 | HIV/AIDS FOCAL PERSON | SW&CD, GENDER DESK, MHD
103 | Social Development | Reduce the incidence of new HIV, AIDS/STIs and other infections, especially among vulnerable groups | Organise Radio Programmes On HIV/AIDs Orientation on HIV/AIDS Stigmatization for Hon. Assembly Members | Municipal Wide | 2 | 3 RADIO PROGRAMMES ORGANIZED All Hon Assembly Members Oriented | 5000 |  | 4000 | HIV/AIDS FOCAL PERSON
104 | Social Development | Co-ordination and Management of Decentralized Response | Stakeholders Meeting | Lartebiokoshie | 2 | 2 STAKEHOLDERS MEETINGS ORGANIZED | 8000 |  | 4000 | HIV/AIDS FOCAL PERSON | COMIITTEE MEMBERS
107 | Social Development | To improve upon the implementation of the 95 95 95 target | To establish DSD services in all the private health facilities Training on DATA CAPTURING TOOLS | Municipal Wide |  | Report | 10000 |  | 2000 | MHD | HIV/AIDS FOCAL PERSON
109 | Social Development | Reduce the incidence of new HIV/AIDS, STIs and other infections among vulnerble groups | Organise debate for some selected JHS Screening For Artisans(Beauticians, hairdressers), Mechanics, Trotro drivers | Mataheko |  | 1debate organised Screening programmes organised for Artisans, Mechanics and Trotro drivers | 8000 |  | 2000 | HIV/AIDS FOCAL PERSON | GES, SW&CD, GENDER DESK, MHD
111 | Social Development | Prevention and behavoral change communication | Organise World AIDs Day | Laterbiokoshie |  | 1 World AIDS Day programme orgnised | 7000 |  | 1000 | HIV/AIDS FOCAL PERSON | MHD
112 | social development | To get adequate and current workable data for the Assembly | Data collection, collation and analyzing | Municipal Wide |  | MESSAP Updated | 24237 |  | 48000 | EHSU | Planning and woks department
114 | social development | To promote basic hygiene in schools, regulate and promote sanitary standards in all public toilets, homes, shops and promote safe food for public consumption. | To conduct education to students, teachers and non- teaching staff. To educate market women, traders and community members on the Assembly’s bye-law, operation clean your frontage activities and regularizing tricycle operators | Municipal Wide | 102 schools | School Health education carried out. Education n organized in all market centers, community members sensitized on their duties and responsibilities as enshrined in the bye-law. | 64000 |  | 130000 | EHSU | Head masters/mistresses, public toilet attendant, Service provider, NADMO, Information services, food handlers, market leaders/queens, traders, religious leaders and procurement.
116 | Socoal Development | To promote basic hygiene and promote safe food for public consumption. | To initiate mass screening and education to food handlers alongside printing of certificates and ceasing and confiscicating expire product. |  | 1611 vendors screened | Mass screening and health education carried out and certificate issued accordingly | 50000 |  | 55000 | EHSU
118 | social development | To promote health and prevent diseases | Public announcement and sensitization on household toilet contruction and acquisition. 2. Operation clean your frontage activities. To conduct education to public toilet attendants. | Municipal Wide | 129 75 toilet attendants | household toilets constructed. 2. People are made to be responsible of their frontages Education carried out to public toilet attendants and certified as such. | 5700 |  | 210000 | EHSU | SPI, Information service, works dept., assembly members, Planning unit, dept of social welfare and community development.
119 | social development | To promote and protect health, and to ensure clean healthy environment | To inspect ALL types of premises including markets. To prosecute recalcitrant sanitation offenders and effect bench warrant arrest | Municipal Wide | 15189 | Quarterly reports Sanitary offenders prosecuted and bench warrants effected | 80000 |  | 160000 | EHSU | Assemblymen, Landlords, Traders
120 | social development | To prevent diseases and promote health | Organize monthly clean up exercise and special clean up exercises, evacuate heaps, drains de-silted and septic tank of public schools dislodge. | Municipal Wide | 18 | Clean up exercise organized municipal wide, Heaps of refuse collected, Tertiary drains improved by 15% and storm drains improved by 25% and all full up septic tanks in public schools dislodged | 300000 |  | 469000 | EHSU | Assembly members, Community members, Private contractors, and Zoom lion
121 | social development | To prevent piled up refuse in the communities | Monitor and evaluate activities of waste management contractors | Municipal Wide | 75 household registered | Container sites improved by 77% and Collection at domestic level improved by 12%. | 100000 |  | 54000 | EHSU | Zoomlion and service providers
122 | social development | To protect and promote health | Disinfection and disinfestation of public places including, public toilets, open drains, container sites etc. | Municipal Wide |  | Disinfection and disinfestation carried out in markets, lorry stations, public toilets, Drains, container sites and other public places. | 50000 |  | 49000 | EHSU | Zoomlion
124 | Economic Development | Diversify and expand the tourism industry for economic development | Participation in Cultural Festivals and Other Customary Activities eg:Homowo Festivals and Exhibition for groups under LED Participation in activities and programs of the Centre for National Culture. Eg. REFAC, NAFAC,ADESA VILLAGE etc | Laterbiokoshie |  | Preserve and Promote Cultural Heritage | 7000 |  | 5000 | CULTURE AND TOURISM DEPARTMENT
131 | Governance, corruption and Public Accountability | To Deepen Decentratralization | Organize Statutory Meetings (General Assembly, Executive Committee, Sub-Committee's, MUSEC, Audit committee, Management etc.) | Laterbiokorshie | 80 | Meeting minutes |  |  | 250000 | Central Admin | HoD's and Assembly Members
132 | Governance, corruption and Public Accountability | To promote community participation in local governance | Stakeholders/community engagement and Sensitization on the mandate of the Assembly in all electoral areas | Municipal-Wide |  | Reports | 175000 |  | 60000 | Central Administration | Human Resource
133 | Governance, corruption and Public Accountability | To ensure good governance and Promote Tourism in the Municipality | Organize National celebrations and Festivals ( Independence day, Homowo festival etc) | Municipal-Wide |  | Reports | 260000 |  | 50000 | Central Admin | all Departments
134 | Governance, corruption and Public Accountability | Ensure motivation of Officers and to ensure good governance | Support Assembly Participation in NALAG activities | Laterbiokorkoshie |  | NALAG supported duly and report prepared. |  |  | 50000 | Administration | Finance
135 | Governance, corruption and Public Accountability | To ensure good governance and build capacity of Assembly Members | Organize inauguration and orientation workshop for Assembly Members | Lartebiokorshie |  | Reports |  |  | 50000 | Central Admiistration | Works Department
136 | Governance, corruption and Public Accountability | For effective monitoring and evaluation To promote smooth running of official vehicles | Protocol activities (monitoring and evaluation teams, etc) Facilitate transport activities (Fuel, maintenance. insurance, tools, other logistics ) | Lartebiokorshie |  | Reports | 130000 |  | 330000 | Central Admin
141 | Governance, corruption and Public Accountability | To promote security and safe environment | Support for Security activities, Electoral Commision and Legal Issues | Lartebiokorshie |  | Reports | 80000 |  | 100000 | Central Administration
142 | Governance, corruption and Public Accountability | To create public awareness of marriage registration, educate Marriage Officers and Officiating Ministers on the various types of marriages in Ghana and its legal implications. | Creating awareness on marriage celebration in the Municipality. Organise skills and training development for the various officers and Officiating Ministers. | AbCMA |  | Reports, Increased Revenue |  |  | 97000 | Central Administration | Marriage Officer and Information Officer
147 | Governance, corruption and Public Accountability | Promote gender based activities in the Municipality | Support for Gender based activities |  |  | Report |  |  | 20000 | Gender Desk Oficcer
148 | Governance, corruption and Public Accountability | To build staff capacity in service delivery | Organize training for Client Service staff on customer relations / service and on service delivered by the Assembly |  |  | Report |  |  | 10000 | Central Administration | Human Resource
150 | Governance, corruption and Public Accountability | To ensure good governance in the Municipality | Support activities of Store, Records Management Unit, Disburse funds to Education, Health. |  |  | Report |  |  | 90000 | Stores | Central Administration
153 | Governance, corruption and Public Accountability | To strenghten local participation and decentralisation | Support activities of Zonal Councils | Municipal-Wide |  | Zonal Council Reports | 74400 |  |  | Central Admiistration | Other Departments

## Sheet2
Governance, corruption and Public Accountability | To Deepen Decentratralization | Organize Statutory Meetings (General Assembly, Executive Committee, Sub-Committee's, MUSEC, Audit committee, Management etc.)
Governance, corruption and Public Accountability | To promote community participation in local governance | Stakeholders/community engagement and Sensitization on the mandate of the Assembly in all electoral areas
Governance, corruption and Public Accountability | To ensure good governance and Promote Tourism in the Municipality | Organize National celebrations and Festivals ( Independence day, Homowo festival etc)
Governance, corruption and Public Accountability | To promote smooth running of official vehicles | Facilitate transport activities (Fuel, maintenance. insurance, tools, other logistics )
Governance, corruption and Public Accountability | Furnish the Records Management Unit to improve their work out put. | Procurement of 2 cabinets for the Records Management Unit
Governance, corruption and Public Accountability | To strenghten local participation and decentralisation | Support activities of Zonal Councils
Economic Development | Diversify and expand the tourism industry for economic development | Participation in activities and programs of the Centre for National Culture. Eg. REFAC, NAFAC,ADESA VILLAGE etc
social development | To prosecute sanitary cases | To prosecute recalcitrant sanitation offenders and effect bench warrant arrest
social development | To promote basic hygiene in schools, regulate and promote sanitary standards in all public toilets, homes, shops and promote safe food for public consumption. | To conduct education to students, teachers and non- teaching staff.
Socoal Development |  | To conduct education to public toilet attendants.
Socoal Development |  | To initiate mass screening and education to food handlers alongside printing of certificates and ceasing and confiscicating expire product.
Socoal Development |  | To educate market women, traders and community members on the Assembly’s bye-law, operation clean your frontage activities and regularizing tricycle operators
social development | To promote health and prevent diseases | Public announcement and sensitization on household toilet contructionand acquisition. 2. Operation clean your frontage activities
social development | To promote and protect health, and to ensure clean healthy environment | To inspect ALL types of premises including markets
social development | To prevent diseases and promote health | Organize monthly clean up exercise and special clean up exercises, evacuate heaps, drains de-silted and septic tank of public schools dislodge.
social development | To prevent piled up refuse in the communities | Monitor and evaluate activities of waste management contractors
social development | To protect and promote health | Disinfection and disinfestation of public places including, public toilets, open drains, container sites etc.
Governance, Corruption and Public Administration | Compensation for staffs who are injured, impaired or suffer deformity in the discharge of their official duties on behalf of the Assembly | Compensation for staffs who are injured, impaired or suffer deformity in the discharge of their official duties on behalf of the Assembly
Social Development | Reduce the incidence of new HIV, AIDS/STIs and other infections, especially among vulnerable groups | Sensitization programme for Adolescents ( In and Out School), Churches and Mosques
Governance, Corruption and Public Administration | Capacity Building Plan Implementation and reporting | Implement on quarterly basis, planned capacity building interventions and submit 4 quarter reports on capacity building to OHLGS through RCC by the end of 31st December 2024
Governance, Corruption and Public Administration | Consultative meeting for the preparatiion of the composite capacity building plan | organise training needs assessment meetings to collate and prepare 2024 composite capacity building plan
Governance, Corruption and Public Administration | TNT for HRM Reports submission at RCC and OHLGS | Prepare and submit 4 quarterly reports on HRM activities
Governance, Corruption and Public Administration | TNT for monthly HRMIS database backups and salary validation reports submission | prepare and submit HRMIS database backups to RCC every month
Governance, Corruption and Public Administration | Monthly Validation of Salaries and Compensation | Staffs salaries, both GOG and IGF validated and worked on timely to ensure prompt payment of salaries
Governance, Corruption and Public Administration | Interview Fees for GOG Staffs Promotions in 2024 | Prepare Promotion register and other documentation in respect of GOG staffs due for promotion in 2024 and submit to RCC
ECONOMIC DEVELOPMENT | Modernise and enhance agricultural production systems | Sensitization on PFJ
ECONOMIC DEVELOPMENT | Promote livestock and poultry development for food security and income generation | To vaccinate 200 dogs and 100 cats against Rabies
ECONOMIC DEVELOPMENT | Enhance the application of science, technology and innovation | AEAs Home and Farm visits to extend improved technologies by Dec. 2024
SOCIAL DEVELOPMENT | 1. Improve and strengthen the policy and legal environment, institutions and systems for child and family welfare. 2. Strengthen social protection for the vulnerable. | 1.Identify and register PWDs and facilitate skills training for PWDs. 2. Facilitate the implementation of LEAP activities. 3.Supervise and monitor the activities of NGOs. 4.Supervise and monitor the activities of Day care centers.
SOCIAL DEVELOPMENT | Promote the rights and welfare of children | Undertake general casework management including support to families and individuals in non-child maintenance case, child abuse, custody and family welfare or reconciliation.
SOCIAL DEVELOPMENT | Prevent and protect children from all forms of violence, abuse, neglect and exploitation. | Liase with the police and also prepare social investigation reports in favour of missing, abandoned or vulnerable children.
SOCIAL DEVELOPMENT | 1.Train junior high school students on menstrual hygiene management. 2. Train youth groups and women group in income generating activities such as confectionery making. | 1.Train junior high school students on menstrual hygiene management. 2. Train youth groups and women group in income generating activities such as confectionery making.
Governance, Corruption and Public Accountability | Maintainance and Servicing | Run maintenance on photo studio,Website,Records management system,Desktops, laptop computers, printers and photocopier machines
Governance, Corruption and Public Accountability | To take stock of Assembly’s Assets | Update the Asset Stock register of the Assembly
Environment, Infrastructure and Human Settlement | to ensure that Green AbCMA is implemented. | Embark on green tree planting exercise. Trim/cut down overgrown trees. Maintenance of trees planted during AbCMA tree planting exercise
Environment, Infrastructure and Human Settlement | To create awareness on various topics concerning COVID-19 and disaster prevention. | Education and sensitization on Disaster prevention & adaptation in schools and communities
Social Development | To appreciate and recognize the efforts of staff. To improve on the reading abilities of learners. To adequately prepare final year students towards the final BECE examination. | Yearly major programs (CODE, ADEOP, Conference, SPAM, CPD, STMIE, My First Day at School, Teacher Awards). Special Competitions (Reading clinics, Spelling B, Quizes, Essay Competitions, etc.). BECE Preparation.
Social Development | To promote quality teaching and learning & Administrative procedures | Monitoring and evaluation of activities in schools. Data collection and collation (School Census).
Social Development | To create rapport with Head teachers and to establish boundaries of the Directorate | Familiarization visits to schools and boundaries of AbCMED. Meetings (Teachers, Headteachers, Stakeholders).
Environment, Infrastructure and Human Settlement | to improve roads and drain facilities | Maintainance of metal Gratings over drains Construction 10km of U-Drains
Government, Corruption and Public Accountability | Ensure responsive governance and citizen participation in the development dialogue | Collaborate with society organization (CSO’s),NGO’S and other Department to organize sensitization and education programmes
Environment, Infrastructure and Human Settlement | to promote infrastructural development in the Municipality | construction of schools / health centre/market/admistration block for AbCMA. Construction of Library and ICT Complex at Blacksmith cluster of schools
Environment, Infrastructure and Human Settlement | Planning, Budgeting, Monitoring and Evaluation | Update Data on existing Public buildings / Developers buildings in the District (Inventory exercise)
Governance, Corruption and Public Accountability | to have a reliable procurement database and foster the purchase of goods and services | Organise 5 tender committee Meetings and prepare & update procurement Plan
Governance, Corruption and Public Accountability | Ensure that monies collected on behalf of the Assembly is duly accounted for. | Undertake field audit of revenue.

## First Qtr
FOR ACTIVITY MATRIX
Activities (Operations) | Location | Baseline | Output Indicators
Lead
Education of citizens on key topics and pandemics(Good Citizenship, Sanitation, Duties of a citizen, Violent Extremism, Political Tolerance and peaceful co-existence, Gender Equality, Outbreak of Choleria and Mlaria , Tax Education, etc.) | Municipal wide | 386 | 16,800 People from FBOs,CBOs,PWDs and Schools Educated by Dec. 2023 | NCCE | Governance, Corruption and Public Accountability
Register all live births and deaths in the Assembly, Replace outdated and missing Birth certificates | Lartebiokorshie | 214 | No. of births and deaths registered by the end of the year | Birth and Deaths | Governance, Corruption and Public Accountability
Gazetting 2024 fee-fixing resolution and rate inputs.Discuss 2025 fee-fixing | Accra |  | Gazetted fee-fixing on file. | Budget | Governance, Corruption and Public Accountability
Update properties and BOP data.Cleaning of valuation data and exhibiting within the municipality. | Municipal wide |  | Revenue Bills produced and distributed | Budget | Governance, Corruption and Public Accountability
Conduct revenue monitoring/ Supervision exercise and review revenue contract | Municipal-wide | 4 | No. of monitoring exercise and review contract reviews undertaken | Finance Dept. | Governance, Corruption and Public Accountability
Prepare and Submit Monthly, Quarterly and Annual Financial Statements | Laterbiokorshie | 13 | No. of Financial Statements prepared and submitted | Finance Dept. | Governance, Corruption and Public Accountability
Personnel Audit | Laterbiokorshie |  | Payroll function is properly controlled and operating efficiently | IAU | Governance, Corruption and Public Accountability
Facilitate the procurement and supply of goods and services | municipal wide |  | office goods and services procured and supplied | procurement Unit | Governance, Corruption and Public Accountability
Organise tender committee Meetings and prepare & update procurement Plan | municipal wide |  | procurement plan updated and in-use | procurement Unit | Governance, Corruption and Public Accountability
Education in Schools, transport stations, etc on Road safety issues Provide and manage Road Safety (road signs and signals) in the Municipality | Muncipal-wide | Nil | 3 Education Programmes organised in schools and transport Terminals | Transport Officer | Governance, Corruption and Public Accountability
Plan, provide and manage on-street parking in the Municipality Collect data and manage operations of Transport operators | Muncipal-wide | Nil | 10 On-Street Parking streets assigned, operationalized and managed. Data on transport operators and vehicles updated and enforcement done. | Transport Officer | Governance, Corruption and Public Accountability
Update Data on existing Public buildings / Developers buildings in the District (Inventory exercise) | Municipal wide |  | Data on buildings in the District updated | Works | Environment, Infrastructure and Human Settlement
initiate the process to prepare EPA permits, screening, integrity reports, Geotech and othe statutory documents, Health & Safety report | Laterbiokorshie |  | Development control activities improved and issues addressed | Works | Environment, Infrastructure and Human Settlement
Facilitate/Supervise the implementation of Public Investment Plan | Laterbiokorshie |  | Projects Drawings, bills of quantities and tender documents prepared. | Works | Environment, Infrastructure and Human Settlement
Facilitate the Acquisition permits for Project | Laterbiokorshie |  | Screening and EPA for all projects done | Works | Environment, Infrastructure and Human Settlement
Maintainance of metal Gratings over drains Construction 10km of U-Drains | Municipal-Wide |  | Metal Gratings maintained 10km U-drains constructed | URD | Environment, Infrastructure and Human Settlement
Collaborate with society organization (CSO’s),NGO’S and other Department to organize sensitization and education programmes | Municipal-Wide | 10 | Sensitization/education report | ISD | Governance, Corruption and Public Accountability
Coordination of Implemengtation of MTDP and Projects through MPCU and faciltate participatory Inspection, M& E of Projects and Programmes, Prepare Project Concept Notes. Preperation of Annual Progress report for 2023 and quaterly progress reports for 2024. | Laterbiokorshie | 9 | Inspection Reports, Monitoring reports and Evaluation reports drafted. 2023 Annual Progress Report perapred and validated and 4 quarterly Progress Reports that tracks implementation of AAP. | MPCU | Implementation, Coordination, Monitoring and Evaluation
Organize Quarterly Town Hall meetings and other Stakeholder engagements | Laterbiokorshie | 5 | 4 Town Hall Meetings held with participation of 1650 residents | MPCU | Government, Corruption and Public Accountability
Facilitate the Preperation of 2025 Composite Annual Action Plan and conduct mid-year review of 2024. Develop Municipal Public Investment Plan and facilitate activities of Entity Project Committee. | Laterbiokorshie | 4 | 2025 Annual Action Plan Drafted , Approved and disseminated . Comprenhensive Public Investment plan detailing all proposed Capital projects for 2022-2025 and approved | MPCU | Implementation, Coordination, Monitoring and Evaluation
Facilitate the planning and implementation Local Economic Development (LED) interventions | Municipal-wide | 28 | Number of LED Activities Implemented | MPCU | Implementation, Coordination, Monitoring and Evaluation
Facilitate the Implementation of Drainage O&M for GARID Project (Conduct Survey on infrastructure and develop Asset register for all Assets; Support for Coordination,Meetings & Monitoring & Evaluation; Develop Drainage Network Map; Conduct Survey of all storm, primary and secondary drains; Prepare O&M; Desilting of underground channels; Replacement of slabs and metal gratings) | Municipal-Wide |  | GARID O&M activities implemented | PIU | Environment, Infrastructure and Human Settlement
Conduct Spatial Planning Committee Meeting and Technical Sub Committee Meetings | Laterbiokoshie |  | Munites and Attendance | PPD | Environment, Infrastructure and Human Settlement
Monitoring of physical developments to ensure conformity with Local Plans | Municipal-Wide |  | Monitoring embarked and monitoring reports prepared | PPD | Environment, Infrastructure and Human Settlement
Monitoring and evaluation of activities in schools. Data collection and collation (School Census). | Municipal-wide |  | Expect that all teachers have reported in their various schools and have updated all forms of school records and administrative procedures. Schools database updated. | GES | Social Development
Familiarization visits to schools and boundaries of AbCMED. Meetings (Teachers, Headteachers, Stakeholders). | Municipal-wide |  | Expect that officers will know the boundaries of operation and also result in collaboration. Meeting Minutes on file. | GES | Social Development
Education and sensitization on climate change and its effects in Communities and Schools. | municipal wide |  | community, school and organizational engagements held. | NADMO | Environment, Infrastructure and Human Settlement
Embark on green tree planting exercise. Trim/cut down overgrown trees. Maintenance of trees planted during AbCMA tree planting exercise | municipal wide |  | tree planting exercise completed. | NADMO | Environment, Infrastructure and Human Settlement
Set up a system for the introduction of new payment systems for payment of Rate, Fees , Fines, statements and distribution of bill electronicall, Start the process for generating and printing of 2024 BOP, property rate and Signage bills | Laterbiokoshie |  | Payment and distribution Systems created,Generating and printing of 2024 BOP, property rate and signage | MIS UNIT | Governance, Corruption and Public Accountability
Run maintenance on photo studio,Website,Records management system,Desktops, laptop computers, printers and photocopier machines | Laterbiokoshie |  | Maintenance done | MIS UNIT | Governance, Corruption and Public Accountability
Update the Asset Stock register of the Assembly | Lartebiokorshie |  | Data on Assets, date purchased, suppliers, and the current state of the asset whether in use or not. | Stats | Governance, Corruption and Public Accountability
Collect and Update existing data of Businesses and properties, NGO’s, schools, Hospitals and religious organizations within the Municipality | Lartebiokorshie |  | Data on public and private schools, health facilities and religious organization also data on businesses and properties | Stats | Governance, Corruption and Public Accountability
Data on security, social lifestyle, PWDs, birth and death, accident etc. Collaborate with statistical service in survey and census | Lartebiokorshie |  | Update Socio-Economic Data based on census, etc | Stats | Governance, Corruption and Public Accountability
1.Identify and register PWDs and facilitate skills training for PWDs. 2. Facilitate the implementation of LEAP activities. 3.Supervise and monitor the activities of NGOs. 4.Supervise and monitor the activities of Day care centers. | Municipal Wide |  | 1.Number of Disabled people who have accessed the fund 2. Number of LEAP beneficiaries increased 3. Number of NGOs activities supervised effectively. 4. Number of Early Childhood centers that have been registered and supervised effectively | Social Welfare Unit | Social Development
Undertake general casework management including support to families and individuals in non-child maintenance case, child abuse, custody and family welfare or reconciliation. | Municipal Wide |  | Number of Child and family welfare cases managed effectively | Social Welfare Unit | Social Development
Liase with the police and also prepare social investigation reports in favour of missing, abandoned or vulnerable children. | Municipal Wide |  | Number of Social investigation in favor of missing and abandoned children managed effectively as well as chid protection issues. | Social Welfare Unit | Social Development
1.Train junior high school students on menstrual hygiene management. 2. Train youth groups and women group in income generating activities such as confectionery making. | Municipal Wide |  | 1.Number of students trained and number of schools reached. 2.Number of women's group trained and number of people reached. | Community Development Unit | Social Development
Compile and Submit 4 Quarterly and 1 annual reports by Dec. 2024 | Laterbiokorshie |  | An annual and 4 quarterly report submitted | AGRIC. Dept. | Economic Development
Train 30 Farmers on Climate Change Approaches | Municipalwide |  | 30 farmers trained | AGRIC. Dept. | Economic Development
Carryout PPR vaccination on small ruminants by December 2024. | Municipalwide |  | Vaccination carried out | AGRIC. Dept. | Economic Development
To vaccinate 200 cattle against CBPP by Dec. 2024 | Municipalwide |  | 200 cattle vaccinated | AGRIC. Dept. | Economic Development
AEAs Home and Farm visits to extend improved technologies by Dec. 2024 | Municipalwide |  | Home and Farm visits conducted | AGRIC. Dept. | Economic Development
Train and Establish 30 Youth in Rabbit Production | Municipalwide |  | 30 Youth trained and established | AGRIC. Dept. | Economic Development
Conduct a gender mapping of activities of all stakeholders to identify their reach, coverage and gaps | Municipalwide |  | Gender Mapping conducted | AGRIC. Dept. | Economic Development
Train and equip 30 women on affordable poultry housing using locally available resources. | Municipalwide |  | Women were trained and equipped | AGRIC. Dept. | Economic Development
A Study tour for Staff and Livestock Farmers on IMO Technologies applied in Livestock Production | Municipalwide |  | Study tour was organized | AGRIC. Dept. | Economic Development
To vaccinate 200 dogs and 100 cats against Rabies | Municipalwide |  | 200 dogs and 100 cats vaccinated | AGRIC. Dept. | Economic Development
Train and Establish 30 PWDs in Mushroom Production | Municipalwide |  | 30 PWDs trained and established | AGRIC. Dept. | Economic Development
Train Staff on Gender in relation to Agriculture and Education on HIV/AIDS | Municipalwide |  | Staff were trained on Gender | AGRIC. Dept. | Economic Development
Train Staff on some common Livestock diseases which affect Productivity of Farmers | Laterbiokorshie |  | Staff trained | AGRIC. Dept. | Economic Development
Sensitization on PFJ | Municipalwide |  | Households | AGRIC. Dept. | Economic Development
Organize 2 trainings and demonstrations for 30 women on Soya Khebab, Soya Milk, Soya meanimix preparation | Municipalwide |  | Women trained | AGRIC. Dept. | Economic Development
Train 30 Females on SOYA Utilization | Municipalwide |  | Women were trained | AGRIC. Dept. | Economic Development
Train and Establish 20 women in Snail Production | Municipalwide |  | Women were trained | AGRIC. Dept. | Economic Development
Implement on quarterly basis, planned capacity building interventions and submit 4 quarter reports on capacity building to OHLGS through RCC by the end of 31st December 2024 | Various |  | At least 92% of Planned Capacity Building Interventions implemented and reported on by 31st December, 2024 | Human Resource | Governance, Corruption and Public Accountability
Prepare and submit 4 quarterly reports on HRM activities | HR Office |  | 4 quarterly HRM reports on all activities submitted by 15th of the first month of the ensuing quarter | Human Resource | Governance, Corruption and Public Accountability
prepare and submit HRMIS database backups to RCC every month | HR Office |  | Submit monthly updated stafflist and HRMIS database backup by 15th of the ensuing month | Human Resource | Governance, Corruption and Public Accountability
Staffs salaries, both GOG and IGF validated and worked on timely to ensure prompt payment of salaries | HR Office |  | 12 monthly salary validation voucher submitted to RCC, Budget Office and Finance Office | Human Resource | Governance, Corruption and Public Accountability
Prepare Promotion register and other documentation in respect of GOG staffs due for promotion in 2024 and submit to RCC | HR Office |  | All affected staffs documentation prepared and submitted to RCC and fees paid twice in a year | Human Resource | Governance, Corruption and Public Accountability
Compensation for staffs who are injured, impaired or suffer deformity in the discharge of their official duties on behalf of the Assembly | Assembly Premises |  | Affected staff supported | Human Resource | Governance, Corruption and Public Accountability
To prosecute recalcitrant sanitation offenders and effect bench warrant arrest | Municipal Wide | 38 | Sanitary offenders prosecuted and bench warrants effected | MEHO, EHOs and Prosecutor | Social Development
To conduct education to students, teachers and non- teaching staff. | Municipal Wide | 102 schools | School Health education carried out. | MEHO & EHOs | Social Development
To conduct education to public toilet attendants. |  | 75 toilet attendants | Education carried out to public toilet attendants and certified as such. |  | Social Development
To initiate mass screening and education to food handlers alongside printing of certificates and ceasing and confiscicating expire product. |  | 1611 vendors screened | Mass screening and health education carried out and certificate issued accordingly |  | Social Development
To educate market women, traders and community members on the Assembly’s bye-law, operation clean your frontage activities and regularizing tricycle operators |  |  | Education n organized in all market centers, community members sensitized on their duties and responsibilities as enshrined in the bye-law. |  | Social Development
Public announcement and sensitization on household toilet contructionand acquisition. 2. Operation clean your frontage activities | Municipal Wide | 129 | household toilets constructed. 2. People are made to be responsible of their frontages | MEHO & EHOs | Social Development
To inspect ALL types of premises including markets | Municipal Wide | 15189 | Quarterly reports | MEHO & EHOs | Social Development
Organize monthly clean up exercise and special clean up exercises, evacuate heaps, drains de-silted and septic tank of public schools dislodge. | Municipal Wide | 18 | Clean up exercise organized municipal wide, Heaps of refuse collected, Tertiary drains improved by 15% and storm drains improved by 25% and all full up septic tanks in public schools dislodged | Top Management, MEHO,EHOS and labourers | Social Development
Monitor and evaluate activities of waste management contractors | Municipal Wide | 75 household registered | Container sites improved by 77% and Collection at domestic level improved by 12%. | MEHO, EHOS and labourers | Social Development
Disinfection and disinfestation of public places including, public toilets, open drains, container sites etc. | Municipal Wide |  | Disinfection and disinfestation carried out in markets, lorry stations, public toilets, Drains, container sites and other public places. | EHSU | Social Development
Organize Statutory Meetings (General Assembly, Executive Committee, Sub-Committee's, MUSEC, Audit committee, Management etc.) | Laterbiokorshie | 80 | Meeting minutes | Central Admin | Governance, Corruption and Public Accountability
Stakeholders/community engagement and Sensitization on the mandate of the Assembly in all electoral areas | Municipal-Wide |  | Reports | Central Administration | Governance, Corruption and Public Accountability
Organize inauguration and orientation workshop for Assembly Members | Lartebiokorshie |  |  | Central Admiistration | Governance, Corruption and Public Accountability
Protocol activities (monitoring and evaluation teams, etc) | Lartebiokorshie |  | Reports | Central Admin | Governance, Corruption and Public Accountability
Facilitate transport activities (Fuel, maintenance. insurance, tools, other logistics ) | Lartebiokorshie |  | Road worthy of vehicles | Central Admiistration | Governance, Corruption and Public Accountability
Preparation of procurement Plan, Tender committee meetings and Evaluation |  |  |  | Central Administration | Governance, Corruption and Public Accountability
Stock taking activities |  |  |  | Stores | Governance, Corruption and Public Accountability
Support activities of Zonal Councils | Municipal-Wide |  | Zonal Council Reports | Central Admiistration | Governance, Corruption and Public Accountability

## Zonal council
S/No | Development Dimension | Objectives | Activities (Operations) | Location | Baseline | Output Indicators | Quarterly Time Schedule |  |  |  | Indicative Budget |  |  |  | Implementing Agency
[7 empty] | 1st | 2nd | 3rd | 4th | DACF | GoG | IGF | Donor | Lead | Collaborating
1 | Governance, corruption and Public Accountability | To Deepen Decentratralization | Data collection and support of bills distribution | Catchment area |  | Improved revenue | [8 empty] | AOZC Office | Budget Unit-AbCMA
2 | Governance, corruption and Public Accountability | Improve transparency and accountability | Payment of Commission Collectors | AbCMA |  | Reports | [6 empty] | 33600 |  | AOZC Office
3 | Governance, corruption and Public Accountability | To Deepen Decentratralization | Organize Six councillors and Sub-committee meetings | Zonal Council Office |  | Reports | [6 empty] | 21500 |  | AOZC Office
4 | Governance, corruption and Public Accountability | Improvement in capacities of Revenue Collectors | Training of Councilors and Revenue Collectors | Zonal Council Office |  | Improvement in capacities of Revenue Collectors |  |  |  |  | 5000 |  |  |  | AOZC Office | HR Department, AbCMA
5 | Governance, corruption and Public Accountability | For smooth running of the office | Payment of annual Office rent | Zonal Council Office |  | Annual Rent duly paid | [6 empty] | 14000 |  | AOZC Office
6 | Governance, corruption and Public Accountability | Improve transparency and accountability | Enforcement of bye laws on sanitation | All three (3) Electoral Areas |  | Reports duly prepared | [8 empty] | AOZC Office
7 | Governance, corruption and Public Accountability | Improve sanitation | Organise Cleanup Exercise | All three (3) Electoral Areas |  | Reports duly prepared |  |  |  |  | 25000 |  | 10000 |  | AOZC Office | Environmental Health Unit,AbCMA
8 | Governance, corruption and Public Accountability | Reduce revenue leakages | Field monitoring of collectors | Zonal Council wide |  | Improved revenue | [6 empty] | 7500 |  | AOZC Office | Internal Audit and Budget Unit, AbCMA
9 | Governance, corruption and Public Accountability | Improve governance, accountability and transparency | organise stakeholders engagement | All three (3) Electoral Areas |  | Reports duly prepared |  |  |  |  | 4000 |  |  |  | AOZC Office | Planning Unit,AbCMA
10 | Governance, corruption and Public Accountability | Improvement in road network | Metal Gratings | All three (3) Electoral Areas |  | Improved roads |  |  |  |  | 7400 |  |  |  | AOZC Office | Works Department
11 | Governance, corruption and Public Accountability | To improve security | supply and installation of streetlights | All three (3) Electoral Areas |  | Improved security |  |  |  |  | 4000 |  |  |  | AOZC Office | Works Department
12 | Governance, corruption and Public Accountability | To improve office environment | Construction of 3 No. urinal facilities | Abossey Okai Market, Mataheko and Nmmeete | [6 empty] | 24000 |  |  |  | AOZC Office | Works Department
13 | Governance, corruption and Public Accountability | For smooth running of the office | Payment of utilities bills | Zonal Council Office | [8 empty] | 13400 |  | AOZC Office
14 | Governance, corruption and Public Accountability | To ensure day-to-day movement and smooth operations of the council | payment of fuel coupons | Zonal Council Office | [8 empty] | 20000 |  | AOZC Office
16 | Governance, corruption and Public Accountability | To ensure day-to-day movement and smooth operations of the council | Repair and Servicing of official vehicle | Zonal Council Office | [8 empty] | 6000 |  | AOZC Office
| SOCIAL DEVELOPMENT | 1. Improve and strengthen the policy and legal environment, institutions and systems for child and family welfare. 2. Strengthen social protection for the vulnerable. | 1.Identify and register PWDs and facilitate skills training for PWDs. 2. Facilitate the implementation of LEAP activities. 3.Supervise and monitor the activities of NGOs. 4.Supervise and monitor the activities of Day care centers. Sensitisation and education of pre-school heads and caregivers on caregiving skills. | Zonal Area |  | 1.Number of Disabled people who have accessed the fund 2. Number of LEAP beneficiaries increased 3. Number of NGOs activities supervised effectively. 4. Number of Early Childhood centers that have been registered and supervised effectively |  |  |  |  | 2000 |  | 3000
| SOCIAL DEVELOPMENT | Promote the rights and welfare of children | 1.Undertake general casework management including support to families and individuals in non-child maintenance case, child abuse, custody and family welfare or reconciliation. 2. Sensitisation on child welfare and non-maintenace cases with DOVVSU. | Zonal Area |  | Number of Child and family welfare cases managed effectively |  |  |  |  | 2000 |  | 2000
| SOCIAL DEVELOPMENT | Prevent and protect children from all forms of violence, abuse, neglect and exploitation. | Liase with the police and also prepare social investigation reports in favour of missing, abandoned or vulnerable children. | Zonal Area |  | Number of Social investigation in favor of missing and abandoned children managed effectively as well as chid protection issues. |  |  |  |  | 1000 |  | 3000
[11 empty] | 74400 |  | 134000

## FOR PPT
Indicative Budget Sum
Economic Development | 1646550.3
Environment, Infrastructure and Human Settlement | 5629361.03
Governance, corruption and Public Accountability | 5515716.22
Social Development | 4201730.57
Implementation, Coordination, Monitoring and Evaluation | 260175.6
IGF | 5500000
DACF | 6026474.5
PWD | 110000
HIV/AIDS | 44830.68
GOG | 3916586.03
MPCF(SIF) | 405000
DACF/RFG | 729495.92
GARID | 521146.6
Economic Development | 31
Environment, Infrastructure and Human Settlement | 16
Governance, corruption and Public Accountability | 62
Social Development | 39
Implementation, Coordination, Monitoring and Evaluation | 5
Total | 153
FIRST QUARTER
Economic Development | 0.17 | 17
Environment, Infrastructure and Human Settlement | 0.1 | 10
Governance, corruption and Public Accountability | 0.32 | 32
Social Development | 0.13 | 13
Implementation, Coordination, Monitoring and Evaluation | 0.04 | 4 | 0.1
76